## form (hidden)
monthly_v2.0

## Instructions and Glossary
Project Tracker - Instructions
| Purpose | The Project Tracker is a tool for capital analysts to capture information about each board's projects. This data provides a line of sight into project progress and details that is critical to both analysts, other folks within the branch, and management. The data gathered here facilitates project accountability and oversight of project milestones and finances.
Instructions
| During Meetings with the Board | When analysts meet with their board to discuss projects, you should use this tool to guide your meetings and capture information. Make sure you update the meeting date on the Monthly Tracker worksheet. You'll notice that this sheet has conditional formatting that greys out the sheet when the meeting date is not set to the current day. This is done so you have a visual reminder to update this date before you talk with your boards. Taking comprehensive minutes is especially important part of your meetings with the boards. The template provides space for you to enter project-specific minutes, as well as a section for minuting any more general information discussed that might not fall under one specific project. The data is scraped regularly and then the template is regenerated with updated information. During this process, minutes are archived and relocated to the far-left side of the template (column BD), sorted with the most recent minutes closest to the left.
| As Needed | If you need to update information at any time other than during a meeting with the board, you are free to do so and the revised information will be captured the next time the data team extracts data from worksheet. Do NOT change the meeting date during any such ad-hoc updates. You should only change the meeting dates when you actually meet with the school board.
| General Information & Error Checking | As mentioned above, the Monthly Update worksheet contains conditional formatting that incentivizes you not to forget to enter a meeting date when you talk with the school board. You will notice that once the meeting date is has passed (i.e., it is something other than the current date), the whole sheet goes grey. This provides a visual cue for you to update the date prior to meeting with your board. The sheet also contains some automatic error checking. Cells contain errors when they are highlighted in purple. To determine the reason for the error, scroll over to columns CY to ES. This section contains the same columns as the main table; cells in this table will only contains text if there is an error. That text will describe the cause of the error in the corresponding cell in the main table.
Within-Budget Acknowledgement Process
| Analyst Checks | Confirm that the board has submitted all necessary documentation: •Class A/B cost estimate •Revised CPBF form that reflects the Class A/B cost estimate. •80% design drawings that align with the cost estimate and approved space template. •Child care floor plan approval letter (if applicable). Ensure that all documents are saved in the appropriate folder on the Share Drive. Once you have checked and confirmed all documents, send an email to the board acknowledging receipt of the pre/post tender package.
| Record Keeping | Create a folder in the following directory: \\csc.ad.gov.on.ca\dfs$\GrpData\CBSD\CAPITAL\STRATEGY\Operations\BOARDS\^Project Commitment\Pre & Post Tender Check-In •The folder should be named using the following naming format: project id # YYYY-MM-DD Example: 12-123 # 2025-12-30 •The date in the folder name should be the date of the email acknowledging receipt of the documents and confirming the board can proceed. •Save the following in the folder you created above: o The CPBF form that reflects the pre-tender/post-tender budget. o The email to the school board (sent within 7 days of the board’s submission) confirming all documents have been submitted and that the ministry has no concerns with the board proceeding to tender/awarding the contract.
Project Tracker Glossary
Overview of the Worksheets within the Project Tracker
| Board Contacts | Use this worksheet to enter the contact information for your boards. This is a central location for Capital Analysts to store this information, as well as a place where management and other analysts can go if they need this information. This is important to support coverage for analysts who are absent.
| Monthly Update | Use this tab to memorialize meetings with the school boards. See instructions above and glossary below for more information.
| Basic Project Info | Use this worksheet to enter the official school name, the school's location information, sign installation information, and the opening ceremony date. See below for a glossary, defining what should be entered in each column.
| Ad-Hoc or Potential Projects | Use this worksheet to enter data about potential projects that have not yet been approved or about ad-hoc, minor projects that don't show up on the Monthly Tracker sheet.
| Project Commitment | This sheet is for your reference only. It is not editable. It provides information about the current project commitment for the projects for this board.
Glossary - Basic Project Info Tab
Section 1: Project Details
Col 1 | Project ID | Automatically generated and uneditable. Each project is assigned a unique ID for tracking throughout its lifecycle. The ID displayed here is the ID for the construction portion of the project.
Col 2 | Project Name | Automatically generated and uneditable. This is the name assigned to the project when it is first approved. It cannot be changed and is constant throughout the project's lifecycle.
Col 3 | Official School Name | Use this field to update the official school name that will be used after the school is open. Please use the complete name and do not use abbreviations (e.g. use "Example Public School" instead of "Example" or "Example P.S.". If this project is an addition, this field can be completed as soon as the project is approved.
Col 4 | Project Type | Automatically generated and uneditable. Project types potentially included in this tracker are: New Construction, Retrofit, Addition, and Purchase.
Col 5 | Project Category | Automatically generated and uneditable. This field identifies the need that is met by the project. Potential project categories that could be included on this tracker are: Accommodation Pressure, Child Care, Facility Condition, Consolidation, and French Language Access.
Col 6 | Address | Enter the address for the school. If it's not yet known, leave it blank.
Col 7 | City | Use this field to enter the city/town where the project is located. This should be known at the time of project approval and be pre-populated on the template. Therefore, this field can be left unedited except for very rare circumstances.
Col 8 | Postal Code | Enter the postal code of the school. If the it's not yet known, leave it blank.
Col 9 | Latitude | Enter the latitude of the school. This information should be updated once the site has been purchased.
Col 10 | Longitude | Enter the longitude of the school. This information should be updated once the site has been purchased.
Section 2: Communications Issues
Col 11 | Sign Installed | Indicate whether the board has installed a sign on the project site.
Col 12 | Opening Ceremony - Date | Use this once the project approaches completion if the board plans an opening ceremony. Otherwise, leave this blank.
Glossary - Monthly Update Tab
Section 1: Project Details
Col 1 | Project ID | Automatically generated and uneditable. Each project is assigned a unique ID for tracking throughout its lifecycle. The ID displayed here is the ID for the construction portion of the project.
Col 2 | Project Name | Automatically generated and uneditable. This is the name assigned to the project when it is first approved. It cannot be changed and is constant throughout the project's lifecycle. The official name of the school can be modified on the Basic Project Info tab.
Col 3 | Meeting Minutes | Enter details about each project based on conversations with the school board.
Col 4 | Project Type | Automatically generated and uneditable. Project types potentially included in this tracker are: New Construction, Retrofit, Addition, and Purchase.
Col 5 | Project Category | Automatically generated and uneditable. This field identifies the need that is met by the project. Potential project categories that could be included on this tracker are: Accommodation Pressure, Child Care, Facility Condition, Consolidation, and French Language Access.
Col 6 | Record Status | This drop-down determines which projects will be removed from your trackers. If you want to remove a project, you must identify whether it has been completed or cancelled. The default is for projects to remain on the tracker. When projects are removed from the tracker, it triggers an email notification to your manager and director.
Col 7 | Construction Status | Automatically generated and uneditable. This field is calculated based on the dates provided to the right in this sheet. If the meeting date is after the opening date, the construction status is "Open"; if the meeting date is after the construction date, the status is "Under Construction". Otherwise the project status is "Planning".
Section 2: Project Commitment Progress
Col 8 | Pre-Tender Submission Date | This is the estimated/actual submission date for the pre-tender budget. This field must be a date value.
Col 9 | Pre-Tender Package Type | Use this dropdown to indicate whether the pretender budget is within existing funding or requires additional ministry funds.
Col 10 | Pre-Tender Package Complete | Automatically generated and uneditable. This indicates whether we have a record of the pre-tender budget in our data system and, if so, the date of the approval (for packages approved by the minister) or notification (for within-budget acknowledgments).
Col 11 | CA Reviewed All Pre-Tender Documents | This is a manual confirmation that the CA has completed their review of the pre-tender package.
Col 12 | Post-Tender Submission Date | This is the estimated/actual submission date for the post-tender budget. This field must be a date value.
Col 13 | Post-Tender Package Type | Use this dropdown to indicate whether the post-tender budget is within existing funding or requires additional ministry funds.
Col 14 | Post-Tender Package Complete | Automatically generated and uneditable. This indicates whether we have a record of the post-tender budget in our data system and, if so, the date of the approval (for packages approved by the minister) or notification (for within-budget acknowledgments).
Col 15 | CA Reviewed All Post-Tender Documents | This is a manual confirmation that the CA has completed their review of the post-tender package.
Section 3: Pre-Tender
Col 16 | Site Ownership Status | Use this dropdown to indicate the site status. Only use "Not Applicable" if the project is an addition/retrofit and does not require a site purchase.
Col 17 | Site Purchase Date | This field must be a date value or blank. Indicate when the board will gain/gained ownership of the site or leave it blank if Site Ownership Status is "Not Applicable".
Col 18 | Site Purchase Date Error Explanation | Use this dropdown to identify the progress on the project's designs.
Col 19 | Design Status | This field must be a date value. Indicate expected/actual date of the space template approval.
Col 20 | Space Template Approval Date | This field must be a date value or blank. Indicate the expected/actual date of the child care floorplan approval. Leave blank only if the project does not include child care.
Col 21 | Child Care Floorplan Approval Date | This field must be a date value. Provide the expected/actual initial site plan submission date.
Col 22 | Child Care Floorplan Approval Date Error Explanation | This field must be a date value. Provide the expected/actual site plan submission date.
Col 23 | Initial Site Plan Submission Date | Use the field only if Col 22 (Child Care Floorplan Approval Date Error Explanation) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 22.
Col 24 | Site Plan Approval Date | This field must be a date value. Enter the expected/actual date the board received a building permit for this project.
Col 25 | Site Plan Approval Date Error Explanation | Use the field only if Col 24 (Site Plan Approval Date) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 24.
Col 26 | Build Permit Obtained Date | This field must be a date value. Enter the expected/actual date the board opened the tender process.
Col 27 | Build Permit Obtained Date Error Explanation | This field must be a date value. Enter the expected/actual date the board closed the tender process.
Section 4: Construction
Col 28 | Tender Issued Date | This field must be a date value. Enter the expected/actual date the board awards the contract to the successful bid.
Col 29 | Tender Closed Date | This field must be a date value. Enter the expected/actual date that construction work will actually begin on the school site. This date must follow all tender dates and the contract awarded date.
Col 30 | Contract Awarded Date | Use the field only if Col 29 (Tender Closed Date) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 29.
Col 31 | Construction Start Date | This field must be a date value. Enter the expected/actual date the project will be substantially complete - that is, the project is complete up to the point that it can be utilized for its intended purpose. Under all but very rare circumstances this date will precede the opening date.
Col 32 | Construction Start Date Error Explanation | Use the field only if Col 31 (Construction Start Date) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 31.
Section 5: Project Completion
Col 33 | Substantial Completion Date | This field must be a date value. Enter the expected/actual date the school portion of the project will be open (i.e., the date when kids will be in new seats).
Col 34 | Substantial Completion Date Error Explanation | Use the field only if Col 33 (Substantial Completion Date) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 33.
Col 35 | School Opening Date | This field must be a date value or blank. Enter the expected/actual date the child care portion of the project will be open (when will the center be taking care of children?). This must be completed unless the project does not include child care.
Col 36 | School Opening Date Error Explanation | Use the field only if Col 35 (School Opening Date ) indicates an error (cell is highlighted in purple) but you believe the information is correct, explain the descrpancy in this cell and it will remove the error formatting in Col 35.
Col 37 | Child Care Opening Date | This field must be a date value. Enter the expected/actual date of financial close out for the project. At this point, all construction is complete, all deficiencies have been addressed and the financial close-out form has been submitted for final budget/cost reconciliation. This is generally 12-18 months after the opening date.
Section 6: Approved Project Funding
Col 38 | Child Care Opening Date Error Explanation | Automatically generated and uneditable.
Col 39 | Financial Close-Out Date | Automatically generated and uneditable.
Col 40 | Funding - All Associated Projects | Automatically generated and uneditable.
Col 41 | Funding - Construction Project | Automatically generated and uneditable.
Col 42 | Funding - Site Acquisition | Automatically generated and uneditable.
Section 7: Projected Cost
Col 43 | Funding - Demolition | Use the drop-down to indicate how the board determined the cost estimate.
Col 44 | Funding - All Other Associated Projects | Enter the board's estimate of the total cost of the construction project. This includes the cost of the school portion, child care portion, site costs, and any other portion not captured in columns 45 to 47
Col 45 | Basis of Cost Estimate | Enter the estimated/actual cost of any land purchase associated with this project. Leave it blank if no land is needed for this project.
Col 46 | Estimated Cost - Construction Project | Use this only if the project will be associated with a separate project ID assigned to a demolition project. This would only happen if the board is demolishing an entire building as part of the project.
Col 47 | Estimated Cost - Land | Use this only in the rare circumstance where there is/will be any other project ID(s) associated with this project.

## Board Contacts
School Board Contact List
Name | Role | Title | Email | Phone
*((tbl*((board_contacts*((col*((name | *((col*((role | *((col*((title | *((col*((email | *((col*((phone

## Basic Project Info
Basic Project Information
Section 1: Project Details | [9 empty] | Section 2: Communications Issues
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 | Col 11 | Col 12
Project ID | Project Name | Official School Name | Project Type | Project Category | Address | City | Postal Code | Latitude | Longitude | Sign Installed | Opening Ceremony - Date
No. de projet | Nom du projet |  | Type de projet | Catégorie de projet
*((tbl*((basic_project_info*((col*((project_id | *((col*((project_name | *((col*((project_name_official | *((col*((project_type | *((col*((project_category | *((col*((location_address | *((col*((location_city | *((col*((location_postal_code | *((col*((location_latitude | *((col*((location_longitude | *((col*((sign_installed | *((col*((date_opening_ceremony
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Monthly Update
Monthly Project Updates |  | *((var*((board_number_name
|  |  |  | *((var*((missing_data_count*((formula*((right | 0
Meeting Date |  | *((var*((date_meeting | [92 empty] | *((var*((error_count*((formula*((down | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE |  | FALSE | FALSE | FALSE |  | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
| General Meeting Minutes: | *((var*((meeting_minutes_general_current | [44 empty] | Historical General Meeting Minutes -------------> |  | *((tbl*((meeting_minutes_general*((col*((meeting_minutes_general_minus_1 | *((col*((meeting_minutes_general_minus_2 | *((col*((meeting_minutes_general_minus_3 | *((col*((meeting_minutes_general_minus_4 | *((col*((meeting_minutes_general_minus_5 | *((col*((meeting_minutes_general_minus_6 | *((col*((meeting_minutes_general_minus_7 | *((col*((meeting_minutes_general_minus_8 | *((col*((meeting_minutes_general_minus_9 | *((col*((meeting_minutes_general_minus_10 | *((col*((meeting_minutes_general_minus_11 | *((col*((meeting_minutes_general_minus_12 | *((col*((meeting_minutes_general_minus_13 | *((col*((meeting_minutes_general_minus_14 | *((col*((meeting_minutes_general_minus_15 | *((col*((meeting_minutes_general_minus_16 | *((col*((meeting_minutes_general_minus_17 | *((col*((meeting_minutes_general_minus_18 | *((col*((meeting_minutes_general_minus_19 | *((col*((meeting_minutes_general_minus_20 | *((col*((meeting_minutes_general_minus_21 | *((col*((meeting_minutes_general_minus_22 | *((col*((meeting_minutes_general_minus_23 | *((col*((meeting_minutes_general_minus_24 | [22 empty] | 97 | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE
Section 1: Project Details | [6 empty] | Section 2: Project Commitment Progress | [7 empty] | Section 3: Pre-Tender | [13 empty] | Section 4: Construction |  |  |  |  | Section 5: Project Completion |  |  |  |  | Section 6: Approved Project Funding |  |  |  |  | Section 7: Projected Cost |  |  |  |  | Section 8: Historical Meeting Minutes | [46 empty] | Error Messages |  |  |  |  | Error Messages | [8 empty] | Error Messages | [5 empty] | Error Messages |  |  |  |  | Error Messages |  |  | Error Messages |  |  | Error Messages |  |  |  |  | Error Messages |  |  |  |  | Error Messages |  |  |  |  | Error Messages
Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 | Col 11 | Col 12 | Col 13 | Col 14 | Col 15 | Col 16 | Col 17 | Col 18 | Col 19 | Col 20 | Col 21 | Col 22 | Col 23 | Col 24 | Col 25 | Col 26 | Col 27 | Col 28 | Col 29 | Col 30 | Col 31 | Col 32 | Col 33 | Col 34 | Col 35 | Col 36 | Col 37 | Col 38 | Col 39 | Col 40 | Col 41 | Col 42 | Col 43 | Col 44 | Col 45 | Col 46 | Col 47 | Col 48 | Col 49 | Col 50 | Col 51 | Col 52 | Col 53 | Col 54 | Col 55 | Col 56 | Col 57 | Col 58 | Col 59 | Col 60 | Col 61 | Col 62 | Col 63 | Col 64 | Col 65 | Col 66 | Col 67 | Col 68 | Col 69 | Col 70 | Col 71 | Col 72 | Col 73 | [23 empty] | Col 1 | Col 2 | Col 3 | Col 4 | Col 5 | Col 6 | Col 7 | Col 8 | Col 9 | Col 10 | Col 11 | Col 12 | Col 13 | Col 14 | Col 15 | Col 16 | Col 17 | Col 18 | Col 19 | Col 20 | Col 21 | Col 22 | Col 23 | Col 24 | Col 25 | Col 26 | Col 27 | Col 28 | Col 29 | Col 30 | Col 31 | Col 32 | Col 33 | Col 34 | Col 35 | Col 36 | Col 37 | Col 38 | Col 39 | Col 40 | Col 41 | Col 42 | Col 43 | Col 44 | Col 45 | Col 46 | Col 47 | Col 48 | Col 49 |  |  |  | Col 11 | Col 11 | Col 11 | Col 11 | Col 15 | Col 15 | Col 15 | Col 15 | Col 16 | Col 16 | Col 16 | Col 16 | Col 17 | Col 17 | Col 17 | Col 17
Project ID | Project Name | Meeting Minutes | Project Type | Project Category | Record Status | Construction Status | Pre-Tender Submission Date | Pre-Tender Package Type | Pre-Tender Package Complete | CA Reviewed All Pre-Tender Documents | Post-Tender Submission Date | Post-Tender Package Type | Post-Tender Package Complete | CA Reviewed All Post-Tender Documents | Site Ownership Status | Site Purchase Date | Site Purchase Date Error Explanation | Design Status | Space Template Approval Date | Child Care Floorplan Approval Date | Child Care Floorplan Approval Date Error Explanation | Initial Site Plan Submission Date | Site Plan Approval Date | Site Plan Approval Date Error Explanation | Build Permit Obtained Date | Build Permit Obtained Date Error Explanation | Tender Issued Date | Tender Closed Date | Contract Awarded Date | Construction Start Date | Construction Start Date Error Explanation | Substantial Completion Date | Substantial Completion Date Error Explanation | School Opening Date | School Opening Date Error Explanation | Child Care Opening Date | Child Care Opening Date Error Explanation | Financial Close-Out Date | Funding - All Associated Projects | Funding - Construction Project | Funding - Site Acquisition | Funding - Demolition | Funding - All Other Associated Projects | Basis of Cost Estimate | Estimated Cost - Construction Project | Estimated Cost - Land | Estimated Cost - Demolition | Estimated Cost - All Other Associated Projects | *((tbl*((meeting_minutes_heading*((col*((meeting_minutes_minus_1 | *((col*((meeting_minutes_minus_2 | *((col*((meeting_minutes_minus_3 | *((col*((meeting_minutes_minus_4 | *((col*((meeting_minutes_minus_5 | *((col*((meeting_minutes_minus_6 | *((col*((meeting_minutes_minus_7 | *((col*((meeting_minutes_minus_8 | *((col*((meeting_minutes_minus_9 | *((col*((meeting_minutes_minus_10 | *((col*((meeting_minutes_minus_11 | *((col*((meeting_minutes_minus_12 | *((col*((meeting_minutes_minus_13 | *((col*((meeting_minutes_minus_14 | *((col*((meeting_minutes_minus_15 | *((col*((meeting_minutes_minus_16 | *((col*((meeting_minutes_minus_17 | *((col*((meeting_minutes_minus_18 | *((col*((meeting_minutes_minus_19 | *((col*((meeting_minutes_minus_20 | *((col*((meeting_minutes_minus_21 | *((col*((meeting_minutes_minus_22 | *((col*((meeting_minutes_minus_23 | *((col*((meeting_minutes_minus_24 |  | *((table_end*((meeting_minutes_heading |  | cc_amount | Site Purchase Date | Space Template Approval Date | Child Care Floorplan Approval Date | Initial Site Plan Submission Date | Site Plan Approval Date | Build Permit Obtained Date | Pre-Tender Submission Date | Tender Issued Date | Tender Closed Date | Post-Tender Submission Date | Contract Awarded Date | Construction Start Date | Substantial Completion Date | School Opening Date | Child Care Opening Date | Financial Close-Out Date |  |  |  | Project ID | Project Name | Meeting Minutes | Project Type | Project Category | Record Status | Construction Status | Pre-Tender Submission Date | Pre-Tender Package Type | Pre-Tender Package Complete | CA Reviewed All Pre-Tender Documents | Post-Tender Submission Date | Post-Tender Package Type | Post-Tender Package Complete | CA Reviewed All Post-Tender Documents | Site Ownership Status | Site Purchase Date | Site Purchase Date Error Explanation | Design Status | Space Template Approval Date | Child Care Floorplan Approval Date | Child Care Floorplan Approval Date Error Explanation | Initial Site Plan Submission Date | Site Plan Approval Date | Site Plan Approval Date Error Explanation | Build Permit Obtained Date | Build Permit Obtained Date Error Explanation | Tender Issued Date | Tender Closed Date | Contract Awarded Date | Construction Start Date | Construction Start Date Error Explanation | Substantial Completion Date | Substantial Completion Date Error Explanation | School Opening Date | School Opening Date Error Explanation | Child Care Opening Date | Child Care Opening Date Error Explanation | Financial Close-Out Date | Funding - All Associated Projects | Funding - Construction Project | Funding - Site Acquisition | Funding - Demolition | Funding - All Other Associated Projects | Basis of Cost Estimate | Estimated Cost - Construction Project | Estimated Cost - Land | Estimated Cost - Demolition | Estimated Cost - All Other Associated Projects
Section 1: Project Details Col 1: No. de projet; Section 1: Project Details Col 2: Nom du projet; Section 1: Project Details Col 4: Type de projet; Section 1: Project Details Col 5: Catégorie de projet; Section 6: Approved Project Funding Col 42: IP; Section 6: Approved Project Funding Col 43: Service de garde; Section 6: Approved Project Funding Col 44: Autre; Section 7: Projected Cost Col 45: Base de l'estimation des coûts; Section 7: Projected Cost Col 49: Coûts du site | [39 empty] | 0
0
*((tbl*((monthly*((col*((project_id | *((col*((project_name | *((col*((meeting_minutes | *((col*((project_type | *((col*((project_category | *((col*((record_status | *((col*((construction_status*((formula*((down | *((col*((date_pretender | *((col*((pretender_package_type | *((col*((pre_tender_complete | *((col*((pre_tender_documents_reviewed | *((col*((date_posttender | *((col*((posttender_package_type | *((col*((post_tender_complete | *((col*((post_tender_documents_reviewed | *((col*((site_status | *((col*((date_site_purchase | *((col*((error_explained_date_site_purchase | *((col*((design_status | *((col*((date_space_template | *((col*((date_cc_floorplan | *((col*((error_explained_date_cc_floorplan | *((col*((date_site_plan_submission | *((col*((date_site_plan_approved | *((col*((error_explained_date_site_plan_approved | *((col*((date_building_permit | *((col*((error_explained_date_building_permit | *((col*((date_tender_issue | *((col*((date_tender_closed | *((col*((date_tender | *((col*((date_construction | *((col*((error_explained_date_construction | *((col*((date_substantial_completion | *((col*((error_explained_date_substantial_completion | *((col*((date_opening | *((col*((error_explained_date_opening | *((col*((date_opening_cc | *((col*((error_explained_date_opening_cc | *((col*((date_completion | *((col*((funding_all*((formula*((down | *((col*((funding_construction | *((col*((funding_site | *((col*((funding_demo | *((col*((funding_other_projects | *((col*((cost_basis | *((col*((cost_estimate_construction | *((col*((cost_estimate_land | *((col*((cost_estimate_demo | *((col*((cost_estimate_other_projects | *((col*((meeting_minutes_minus_1 | *((col*((meeting_minutes_minus_2 | *((col*((meeting_minutes_minus_3 | *((col*((meeting_minutes_minus_4 | *((col*((meeting_minutes_minus_5 | *((col*((meeting_minutes_minus_6 | *((col*((meeting_minutes_minus_7 | *((col*((meeting_minutes_minus_8 | *((col*((meeting_minutes_minus_9 | *((col*((meeting_minutes_minus_10 | *((col*((meeting_minutes_minus_11 | *((col*((meeting_minutes_minus_12 | *((col*((meeting_minutes_minus_13 | *((col*((meeting_minutes_minus_14 | *((col*((meeting_minutes_minus_15 | *((col*((meeting_minutes_minus_16 | *((col*((meeting_minutes_minus_17 | *((col*((meeting_minutes_minus_18 | *((col*((meeting_minutes_minus_19 | *((col*((meeting_minutes_minus_20 | *((col*((meeting_minutes_minus_21 | *((col*((meeting_minutes_minus_22 | *((col*((meeting_minutes_minus_23 | *((col*((meeting_minutes_minus_24 |  |  | *((col*((site_ownership_formula*((formula*((down | *((col*((scope_cc_spaces_added | *((col*((temp_formula_78*((formula*((down | *((col*((temp_formula_79*((formula*((down | *((col*((temp_formula_80*((formula*((down | *((col*((temp_formula_81*((formula*((down | *((col*((temp_formula_82*((formula*((down | *((col*((temp_formula_83*((formula*((down | *((col*((temp_formula_84*((formula*((down | *((col*((temp_formula_85*((formula*((down | *((col*((temp_formula_86*((formula*((down | *((col*((temp_formula_87*((formula*((down | *((col*((temp_formula_88*((formula*((down | *((col*((temp_formula_89*((formula*((down | *((col*((temp_formula_90*((formula*((down | *((col*((temp_formula_91*((formula*((down | *((col*((temp_formula_92*((formula*((down | *((col*((temp_formula_93*((formula*((down | [5 empty] | *((col*((temp_formula_99*((formula*((down |  |  |  |  | *((col*((temp_formula_104*((formula*((down | *((col*((temp_formula_105*((formula*((down |  | *((col*((temp_formula_107*((formula*((down | *((col*((temp_formula_108*((formula*((down | *((col*((temp_formula_109*((formula*((down |  | *((col*((temp_formula_111*((formula*((down | *((col*((temp_formula_112*((formula*((down | *((col*((temp_formula_113*((formula*((down |  | *((col*((temp_formula_115*((formula*((down | *((col*((temp_formula_116*((formula*((down | *((col*((temp_formula_117*((formula*((down |  | *((col*((temp_formula_119*((formula*((down | *((col*((temp_formula_120*((formula*((down |  | *((col*((temp_formula_122*((formula*((down |  | *((col*((temp_formula_124*((formula*((down | *((col*((temp_formula_125*((formula*((down | *((col*((temp_formula_126*((formula*((down | *((col*((temp_formula_127*((formula*((down |  | *((col*((temp_formula_129*((formula*((down |  | *((col*((temp_formula_131*((formula*((down |  | *((col*((temp_formula_133*((formula*((down |  | *((col*((temp_formula_135*((formula*((down | [5 empty] | *((col*((temp_formula_141*((formula*((down | *((col*((temp_formula_142*((formula*((down | *((col*((temp_formula_143*((formula*((down | *((col*((temp_formula_144*((formula*((down | *((col*((temp_formula_145*((formula*((down |  |  |  | *((col*((temp_formula_149*((formula*((down | *((col*((temp_formula_150*((formula*((down | *((col*((temp_formula_151*((formula*((down | *((col*((temp_formula_152*((formula*((down | *((col*((temp_formula_153*((formula*((down | *((col*((temp_formula_154*((formula*((down | *((col*((temp_formula_155*((formula*((down | *((col*((temp_formula_156*((formula*((down | *((col*((temp_formula_157*((formula*((down | *((col*((temp_formula_158*((formula*((down | *((col*((temp_formula_159*((formula*((down | *((col*((temp_formula_160*((formula*((down | *((col*((temp_formula_161*((formula*((down | *((col*((temp_formula_162*((formula*((down | *((col*((temp_formula_163*((formula*((down | *((col*((temp_formula_164*((formula*((down
Section 6: Approved Project Funding Col 40: 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Meeting Minutes cannot be blank |  |  |  |  | Pre-Tender Submission Date cannot be blank | Pre-Tender Package Type cannot be left blank. |  | Confirm you reviewed the pretender checkin documents | Post-Tender Submission Date cannot be blank | Post-Tender Package Type cannot be left blank. |  | Confirm you reviewed the post tender check-in documents | Site Ownership Status cannot be blank | Site Purchased Date cannot be blank |  | Design Status cannot be blank | Space Template Approval Date cannot be blank |  |  | Initial Site Plan Submission Date cannot be blank | Site Plan Approval Date cannot be blank |  | Build Permit Obtained Date cannot be blank |  | Tender Issued Date cannot be blank | Tender Closed Date cannot be blank | Contract Awarded Date cannot be blank | Construction Start Date cannot be blank |  | Substantial Completion Date cannot be blank | [5 empty] | Financial Close-Out Date cannot be blank | [5 empty] | Basis of Cost Estimate cannot be blank | [7 empty] | Confirm you reviewed the pretender checkin documents |  | Confirm you reviewed the pretender checkin documents |  | Confirm you reviewed the post tender check-in documents |  | Confirm you reviewed the post tender check-in documents |  | Site Ownership Status cannot be blank | Site Ownership Status cannot be blank |  | Site purchase date is in the past, but site ownership status indicates site has not yet been purchaseed | Site Purchased Date cannot be blank | Site Purchased Date cannot be blank | Site Ownership Status cannot be blank
[73 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | bar: Section 1: Project Details Col 1 to Section 8: Historical Meeting Minutes Col 73

## Ad-Hoc or Potential Projects
Ad-hoc & Potential Projects
Parent ID | Project ID | Project Name | Submission Type | Project Type | Year Open | Project Category | Project Type | Timing | Cost | Funding Source | Comments
| 99-123 | Example Project | Ad Hoc | Land | 2025 | Accommodation Pressure | Land

## Project Commitment
Project Commitments
English | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Info |  | Key Milestones
Project ID | Project Name | Site Purchase | Space Template Approved | Site Plan Approved | Pre-Tender Checkin | Tender Approved | Post-Tender Checkin | Construction Start | Substantial Completion | School/Addition Opening | Financial Close | Site Purchase Date | Space Template Approval Date | Child Care Floorplan Approval Date | Initial Site Plan Submission Date | Site Plan Approval Date | Build Permit Obtained Date | Pre-Tender Submission Date | Tender Issued Date | Tender Closed Date | Post-Tender Submission Date | Contract Awarded Date | Construction Start Date | Substantial Completion Date | School Opening Date | Child Care Opening Date | Financial Close-Out Date
*((tbl*((pc*((col*((project_id | *((col*((project_name | *((col*((date_site_purchase | *((col*((date_space_template | *((col*((date_site_plan_approved | *((col*((date_pretender | *((col*((date_tender | *((col*((date_posttender | *((col*((date_construction | *((col*((date_substantial_completion | *((col*((date_opening | *((col*((date_completion | *((col*((date_site_purchase_comparison*((formula*((down | *((col*((date_space_template_comparison*((formula*((down | *((col*((date_site_plan_approved_comparison*((formula*((down | *((col*((date_pretender_comparison*((formula*((down | *((col*((date_tender_comparison*((formula*((down | *((col*((date_posttender_comparison*((formula*((down | *((col*((date_construction_comparison*((formula*((down | *((col*((date_substantial_completion_comparison*((formula*((down | *((col*((date_opening_comparison*((formula*((down | *((col*((date_completion_comparison*((formula*((down | *((col*((date_site_purchase_comparison*((formula*((down_comparison*((formula*((down | *((col*((date_space_template_comparison*((formula*((down_comparison*((formula*((down | *((col*((date_site_plan_approved_comparison*((formula*((down_comparison*((formula*((down | *((col*((date_pretender_comparison*((formula*((down_comparison*((formula*((down | *((col*((date_tender_comparison*((formula*((down_comparison*((formula*((down | *((col*((date_posttender_comparison*((formula*((down_comparison*((formula*((down
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Constants (hidden)
Constants
Orange Date | -273.75
Red Date | -365

## List (hidden)
Actual/Estimated | Language | Construction Status | Phase | Yes / No | Site Ownership Status | Design Status | Cost Basis | Design | Site Plan | Project Category | Project Type | Package Type
Actual | English | Planning | 1 | Yes | No Site Identified | <30% Complete | Based on estimate of $/sq ft | New | Yes | Accommodation Pressure | Land | Within Budget
Estimate | French | Pre-Procurement | 1 | No | Site Identified Only | 30%-80% Complete | Based on repeat design | Repeat | No | Facility Condition | New School | Additional Funding Required
|  | Tender Issuance | 1 | Not Applicable | Site Under Option Agreement | >80% Complete | Based on Class C or lower Cost Report | EDU Catalogue |  | School Consolidation | Addition | Not Applicable
|  | Tender Closed | 1 |  | Site Purchased |  | Based on Class A or B Cost Report |  |  | French Language Access | Renovation | Not Yet Known
|  | Contract Awarded | 1 |  | Site Purchased Prior to Capital Approval |  | Based on Tender Results |  |  | Other | Disposition
|  | Site Preparation | 2 |  | Not Applicable | [5 empty] | Demolition
|  | Construction | 2 | [7 empty] | Purchase
|  | Substantial Completion | 3 | [7 empty] | Other
|  | Completion | 4
Cost Reconciliation
% Construction Progress |  | Phase (List) | Project Status | Submission Type | Project Risks | Risk Rating | Site Funding Source | Mitigation Strategies | Sign Installed
10 |  | 0 | In Progress | CP | Cost | Low | EDC | Accept | Yes
20 |  | 1 | Remove from tracker (Cancelled) | Ad Hoc | Delay | Medium | LP | Mitigate | No
30 |  | 2 | Remove from tracker (Complete) |  | Delay/Cost | High | LP/EDC | Transfer | No Site Purchased
40 |  | 3 | [5 empty] | Avoid
50 |  | 4 |  |  | Market Risk
60 |  |  |  |  | Governance Risk
70 |  |  |  |  | Organization/Project Management Risk
80 |  |  |  |  | Design Risk
90 |  |  |  |  | Procurement/Tender Risk
100 |  |  |  |  | Site Readiness/Enabling Works
Permit, Licenses and Approvals
Type of Design |  |  |  |  | Construction Risk
New |  |  |  |  | Testing and Commissioning
Repeat
Catalogue
Primary Contact
Senior Buisness Official
Director of Education
Finance Contact
Construction/Project Management Contact

## Translation (hidden)
English
Output | English | French
Monthly Update Sheet
Meeting Date | Meeting Date
Section 1: Project Details | Section 1: Project Details | Détails associés aux projets
Project ID | Project ID
Project Name | Project Name
Address | Address
City | City
Postal Code | Postal Code
Project Type | Project Type
Approval Period | Approval Period
Project Category | Project Category
Project Status | Project Status
Construction Status | Construction Status
Section 2: Square Footage Specification | Section 2: Square Footage Specification
Anticipate Design Change? | Anticipate Design Change?
Square Footage of New Construction | Square Footage of New Construction
Square Footage of Renovaton/Retrofit | Square Footage of Renovaton/Retrofit
Square Footage of Demolition | Square Footage of Demolition
Square Footage of New Child Care | Square Footage of New Child Care
Square Footage of Community Space | Square Footage of Community Space
Square Footage of EarlyOn | Square Footage of EarlyOn
Section 3: Phase 1 - Pre-Tender | Section 3: Phase 1 - Pre-Tender
Site Ownership Status | Site Ownership Status
Site Purchase Date | Site Purchase Date
Space Template Approval Date | Space Template Approval Date
Type of Design Used | Type of Design Used
Design Status | Design Status
Class A/B Cost Estimate -Date | Class A/B Cost Estimate -Date
Child Care Floorplan Approval - Date | Child Care Floorplan Approval - Date
Site, Design and Child Care Related Comments: Include details of scope change if applicable | Site, Design and Child Care Related Comments: Include details of scope change if applicable
Section 4: Phase 2 - Tender | Section 4: Phase 2 - Tender
Tender Issued Date | Tender Issued Date
Tender Closed | Tender Closed
Site Plan Submission Date | Site Plan Submission Date
Site Plan Approval Date | Site Plan Approval Date
Section 5: Phase 3 - Construction | Section 5: Phase 3 - Construction
Construction Start - Date | Construction Start - Date
% Construction Progress | % Construction Progress
Substantial Completion | Substantial Completion
Section 6: Phase 4 - Project Completion | Section 6: Phase 4 - Project Completion
School Opening Date | School Opening Date
Child Care Opening Date | Child Care Opening Date
Project Reconciliation | Project Reconciliation
Section 7: Approved Project Funding | Section 7: Approved Project Funding | Financement approuvé du projet
LP/EDC | LP/EDC
CP | CP
CC | CC
Other | Other
Total Approved Funding | Total Approved Funding
Section 8: Projected Construction Cost | Section 8: Projected Construction Cost | Coût prévu du projet
Basis of Cost Estimate | Basis of Cost Estimate
Land Cost | Land Cost
Building Cost - School | Building Cost - School
Soft Costs - School | Soft Costs - School
Building Cost - Child Care | Building Cost - Child Care
Soft Costs -Child Care | Soft Costs -Child Care
Unique Site Costs - School | Unique Site Costs - School
Unique Site Costs - Child Care | Unique Site Costs - Child Care
Unique Site Costs - Other | Unique Site Costs - Other
Municipal/Extraordinary Cost - School | Municipal/Extraordinary Cost - School
Municipal/Extraordinary Cost - Child Care | Municipal/Extraordinary Cost - Child Care
Municipal/Extraordinary Cost - Other | Municipal/Extraordinary Cost - Other
Total | Total
Variance | Variance
Revised Funding Request | Revised Funding Request
Section 9: Communications Protocol | Section 9: Communications Protocol
Signage | Signage
Opening Ceremony - Date | Opening Ceremony - Date
Section 10: General Comments | Section 10: General Comments | Commentaires
Section 10: Project Risks and Mitigation Stategies | Section 10: Project Risks and Mitigation Stategies
Risk Type | Risk Type
Risk Rating | Risk Rating
Risk Exposure Start Date | Risk Exposure Start Date
Min-Max Cost of Risk ($M) | Min-Max Cost of Risk ($M)
Min-Max Delay of Risk (Months) | Min-Max Delay of Risk (Months)
Mitigation Stategies/Comments | Mitigation Stategies/Comments
CA Comments | CA Comments
Contract Awarded | Contract Awarded
Build Permit Obtained | Build Permit Obtained
Site Preparation Cost | Site Preparation Cost
Site Funding Source | Site Funding Source
Site Prep/Mobilization | Site Prep/Mobilization
Building Cost - Other | Building Cost - Other
ALL ESTIMATED DATES = UNBOLDED ALL ACTUAL DATES = BOLDED | ALL ESTIMATED DATES = UNBOLDED ALL ACTUAL DATES = BOLDED
0
0
0
Output | English | French
Project Commitment
Label Out | Label English | Label French
Project Info | Project Info
Key | Key
Project ID | Project ID | Identification du projet
Project Name | Project Name | Nom du projet
Phase 1 - Start | Phase 1 - Start | Phase 1 - Début
Phase 1 - End | Phase 1 - End | Phase 1 - Fin
Phase 2 - Start | Phase 2 - Start | Phase 2 - Début
Phase 2 - End | Phase 2 - End | Phase 2 - Fin
Phase 3 - Start | Phase 3 - Start | Phase 3 - Début
Phase 3 - End | Phase 3 - End | Phase 3 - Fin
Phase 4 - Start | Phase 4 - Start | Phase 4 - Début
Phase 4 - End | Phase 4 - End | Phase 4 - Fin
Phase Dates | Phase Dates | Dates de phase
Key Milestones | Key Milestones | Étapes Clés
Site Purchase | Site Purchase | Achat du site
Space Template Finalized | Space Template Finalized | Gabarit des espaces finalisé
Signed Joint Use Agreement | Signed Joint Use Agreement
80% Design | 80% Design | Design à 80%
Class A Cost Estimate | Class A Cost Estimate | Rapport du consultant en coûts de classe A
Site Plan Approval | Site Plan Approval | Approbation du plan de site
Build Permit Obtained | Build Permit Obtained | Permis de construire obtenu
Tender Issued | Tender Issued | Projet soumissionné
Construction Start | Construction Start | Début de la construction
School/Addition Opening | School/Addition Opening | école/ajout ouverte
Project Reconciliation | Project Reconciliation | Réconciliation du projet
Funding Requested | Funding Requested | Financement demandé
Cost of Project (Excluding Site) | Cost of Project (Excluding Site) | Coût du projet (Excluant coût du site)
Total Cost of Project (Including Site) | Total Cost of Project (Including Site) | Coût total
Total CP Request | Total CP Request
Total Child Care Request | Total Child Care Request